## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Event Recommender
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 20/7/2020 | Deadline not kept. | Project Management | Delay in implementation | Consider margin of error in scheduling | Analyze requirements properly and estimate time required | Project Manager | Closed | None
2 | 17/07/2020 | Insufficient data available. | Technical | Incorrect classification of events. | Check if data is sufficient or not for system to work | Creation of dataset. | Project Manager | Closed | None
3 | 18/07/2020 | Less accurate predictions | Technical | Incorrect classification of events. | Consider and compare all possible models. | select model with max accuracy | Project Manager | Closed | None
4 | 19/07/2021 | Biased Classification | Technical | Same classification many times | Adjust dataset accordingly. | Balance the dataset | Project Manager | Closed | None