## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Recommender System for Employees
PROJECT SPONSOR | Cloud Counselage
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/20
EXPECTED COMPLETION DATE | 31/07/20
ESTIMATED COST
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | To automatically classify and recommend events to employees based on employee preferences.
BUSINESS CASE | Cloud Counselage receives invites for events in multiple domains that need to be forwarded to people with relevant interests. This task is repetitive and time consuming. Because of manual mistakes sometimes the proper employees won't get proper invites. One often misses events of interest sheerly due to a lack of awareness at the right time. Hence to reduce the manual repetitive task and avoid human problems and mistakes the machine learning based event recommender system is efficient and optimal solution in terms of cost, labor and time.
GOALS/METRICS | To create a recommender system that recommends employees events based on their preferences automatically.
EXPECTED DELIVERABLES | A recommender system that will automatically recommend relevant events to employees.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Take event list as a input,Classify Events, Recommend Event, create list of recommended employees.
OUTSIDE OF SCOPE | Recommendation based on data of other employees (Collaborative).
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Chaitanya Deshpande
SUPPORT RESOURCES | Employee dataset, document templates
SPECIAL NEEDS | None
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Chaitanya Deshpande
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Resource unavailability can cause delay in delivery of project. Going out of scope of project can cause loss of time and efficiency. Misunderstanding of requirements and problem can cause unexpected outcomes and loss of productivity. Improper approach can cause loss in time as well as efforts. Unavailabilty of resources can cause delay.
ASSUMPTIONS | The scope of project is fixed and won't be expanded. The requirement won't change over period of time. Resources will be available without any delay. Schedule of project won't be altered due to external factors.
CONSTRAINTS | Time limit of 7 weeks. Limited resources. Too many available approaches but only few are optimal approaches.