## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Event Recommender System
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-07
PROJECT DELIVERABLE | Event Recommendations for Employees |  | EXECUTION PHASE END DATE: |  | 2020-07-27
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-06-15
OVERALL PROGRESS
SL No | TASK NAME | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identifying the Problem |  | 15/06/2020 | 16/06/2020 | 1 | COMPLETED
| 1.2 Understanding the problem |  | 16/06/2020 | 18/06/2020 | 2 | COMPLETED
| 1.3 Requirement Gathering |  | 18/06/2020 | 20/06/2020 | 2
| 1.4 Creating Project Charter |  | 22/06/2020 | 24/06/2020 | 2 | COMPLETED
| 1.4 Creating SRS Document |  | 25/06/2020 | 28/06/2020 | 3
| 2 Planning |  |  |  |  | COMPLETED
| 2.1 Creating Project Plan |  | 30/06/2020 | 2020-03-07 | 4 | COMPLETED
| 2.2 Effort Estimation |  | 29/06/2020 | 30/06/2020 | 1 | COMPLETED
| 2.3 Creating Schedule |  | 2020-03-07 | 2020-04-07 | 1 | COMPLETED
| 2.4 Creating Test Plan |  | 2020-03-07 | 2020-05-07 | 2 | COMPLETED
3 Execution
| 3.1 Finalize Design |  |  |  |  | COMPLETED
| 3.2 Build |  |  |  |  | COMPLETED
| 3.2.1 Data Preprocessing and cleaning |  | 2020-06-07 | 2020-08-07 | 2 | COMPLETED
| 3.2.2 Creating Training Dataset |  | 2020-08-07 | 2020-12-07 | 4 | COMPLETED
| 3.2.3 Training Classifiers Based on training data and calculating accuracy |  | 13/07/2020 | 18/07/2020 | 5 | COMPLETED
| 3.2.4 Selecting Classifier based on accuracy |  | 18/07/2020 | 19/07/2020 | 1 | COMPLETED
| 3.2.5 Creating data vectors and calculating Cosine similarity |  | 20/07/2020 | 21/07/2020 | 1 | COMPLETED
| 3.2.6 Creating recommendation list |  | 21/07/2020 | 23/07/2020 | 2 | COMPLETED
| 3.3 Testing |  |  |  |  | COMPLETED
| 3.3.1 Unit Testing |  | 23/07/2020 | 24/07/2020 | 1 | COMPLETED
| 3.3.2 Integration Testing |  | 24/07/2020 | 26/07/2020 | 2 | COMPLETED
4 Closure
| 4.1 Project Handover |  | 27/07/2020 | 31/07/2020 |  | COMPLETED