## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 0 | 3 | 1 | 0 | 0
| Project title: | Event Recommender |  | Project Id: |  | Project Manager: | Jayanth G S |  |  | Assumption | 2 | 0 | 0 | 1 | 0 | 0
[10 empty] | Issue | 3 | 0 | 2 | 1 | 0 | 0
|  |  |  | Last Updated date: | 28/07/2020 | Project Team Lead: | Aarya Bodhankar |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 9 |  |  |  |  | 8
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Updates in database are not reflected in given dataset. | Impact on the project performance. | Have a dedicated maintenance team for the project . | Project Manager | High |  | Open | Risk
2 | Risk | Imbalnced data for training classifier. | Biased classification of events. | Balance dataset by adding or removing data points. | Project Manager | High |  | Open | Assumption
3 | Risk | Events involving with multiple domain and events in a single instant. | Different domains within a single instant would me missed out. | Efficient key word extraction algorithm. | Project Manager | High |  | Open | Issue
4 | Risk | Bad maintenance of system | Impact on system performance | Have a adequate maintenance team for the project | Project Manager | Moderate |  | Open | Dependency
5 | Assumption | The domains of employees is correct in which they are working or having interest | The events get recommended accurately. | Have a well crossed checked before analysis | Project Manager | Moderate |  | Open
6 | Assumption | Available dataset is sufficent for predictions. | Impact on the recommendation | Analyze the data and adjust dataset accordingly. | Project Manager | Moderate |  | Closed | Open
7 | Issue | Low Accuracy of the model | Impact on the recommendation | get adequate data and choose perfect model | Project Manager | High |  | Open | Closed
8 | Issue | Inadequate data for training the model | Bad recommendation of employees | get or create data points | Project Manager | High |  | Open
10 | Issue | Event description inadequate | Inappropriate classification | Remove datapoint or update datapoint | Project Manager | Moderate |  | Open | High
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24
Note on D12: HP: